## Sheet1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2022-11-21 | 2022-11-23 | 100% | Hanh | 2022-11-27 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
Logo |  |  | 50% | Hanh |  | 2020-12-14 | 50% | Nhật Trường | Đã xong layout, đã xong responsive
Navbar | 2019-05-23 | 2019-07-01 | 90% | Hanh |  | 2020-12-14 | 90% | Nhật Trường | Đã xong layout, đã xong responsive
Submenu | 2019-05-23 | 2019-05-31 | 100% | Hanh |  | 2020-12-14 | 100% | Nhật Trường | Đã xong layout, đã xong responsive
Search form | 2019-06-20 | 2019-06-28 | 90% | Hanh |  | 2020-12-14 | 90% | Nhật Trường | Đã xong layout, đã xong responsive
Login popup | 2019-06-25 | 2019-07-01 | 80% | Hanh |  | 2020-12-14 | 80% | Nhật Trường | Đã xong layout, đã xong responsive
content 1 | 2022-11-24 | 2022-11-24 | 100% | Hanh | 2022-11-27 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
content 2 | 2022-11-24 | 2022-11-25 | 100% | Hanh | 2022-12-14 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
About | 2022-11-29 | 2022-11-30 | 100% | Hanh | 2022-12-14 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
Outstanding | 2022-12-03 | 2022-12-05 | 100% | Hanh | 2022-12-14 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
Categories | 2022-12-07 | 2022-12-10 | 100% | Hanh | 2022-12-14 | 2022-12-14 | 100% | Tường | Đã xong layout, đã xong responsive
Features | 2022-11-21 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Contact | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Statics | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Video | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Blog | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Testimonials | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive
Footer | 2022-12-02 | 2022-12-02 | 100% | Tường | 2022-12-13 | 2022-12-15 | 100% | Hanh | Đã xong layout, đã xong responsive